## Sheet1
Solicitation Number: FA441726R0015 Project Number: Project Name: Replace Roof B90232, Hurlburt Field, FL Technical Inquiries Due: Tuesday, 28 April 2026 / 1 P.M
PPI Number | Submission Date | Reference | Question | Government Response
1 | 2026-04-28 |  | Is the existing roof a retrofit roof installed over the original built-up roofing system? Please confirm whether the original BUR was left in place beneath a later SSMR retrofit or fully removed. | Yes, there was a renovation project title "1996_FETV 93-1005A-B Add-Alt Rpr Physical Fitness Center See Folder attached.
2 | 2026-04-28 |  | Are more recent as-built drawings available? The drawings provided in Attachment 2 appear to be the original 1975 construction documents for the gymnasium addition and show a 4-ply built-up roof. They do not reflect the current SSMR assembly or any subsequent renovations. Please also confirm the existing roof composition: deck type, number of insulation layers, insulation type and thickness, underlayment, and slip sheet. | Yes, attached is one of many we will share all of our as-builts with all contractors. There are a few originals plans and add-on projects.
3 | 2026-04-28 |  | What percentage of the fascia and soffit metal beam support system should be carried in the proposal for replacement? Without visibility into existing conditions, please provide a budgetary percentage or allowance so all offerors price the same assumption. | 100% replacement. See updated SOW.
4 | 2026-04-28 |  | A roof access hatch was identified during the 17 April site visit. Is this hatch to be replaced, reused and re-flashed, or permanently sealed shut under the new roof system? | Yes, replace roof hatch and access ladder.
5 | 2026-04-28 |  | Portions of the existing roof panels run continuously down the exterior walls and function as wall panels. Please confirm these continuous roof-to-wall panels are included in the replacement scope. | Yes, they are included in the replacement intent.
6 | 2026-04-28 |  | The original SOW (20 Feb 26) required the contractor to "provide and install new lightning protection system." The revised SOW (21 Apr 26) states that the contractor shall "restore the lightning protection system to full operational status using a combination of salvaged and new components." During the site visit no existing LPS was observed on the roof. Please confirm the government's intent — is a new, complete LPS to be furnished and installed as part of this project, including certification? | Yes, I have included in the Final SOW to install a new lightning Protection system price the system into your estimate.
7 | 2026-04-28 |  | Please confirm a laydown area near the building will be allowed. | It will be near the facility after consulting with the user and agreed upon location with the user, contractor and PM
8 | 2026-04-28 |  | What insulation R-value is required for the new roof assembly? The SOW calls for new insulation over the entire deck but does not specify R-value, thickness, or product. Please confirm the minimum R-value | At minimum R-25 and R-35 that pertains to our climate zone.
9 | 2026-04-28 |  | Is weekend work allowed? | Contractor may request weekend or extended hours. Must be submitted by email to the Contracting Officer.
10 | 2026-04-28 |  | What quantity or percentage of roof deck replacement should be carried in the proposal? | Plan on at lease 25% of the entire area of the roof system.
11 | 2026-04-28 |  | The existing roof-to-wall flashing is installed behind the exterior wall panels. To install new flashing, the wall panels (and adjacent wall louvers) will either have to be removed and reinstalled or cut. Please confirm the government's intent: (a) retain existing wall panels and louvers — contractor to carefully remove and reinstall; (b) cut and patch in place; or (c) include replacement of the affected wall panels and louvers in the proposal. Please clarify so this scope can be priced accurately. | The governments intent is replace all SSMR wall panels with new. So you can have access to all flashing areas.
12 | 2026-04-28 |  | Has any hazardous materials testing been performed on the existing roof assembly (asbestos in the original built-up roof, mastics, flashings, or caulks; lead in paint on metal trim or flashings)? If so, please provide the survey results. If not, please confirm who is responsible for testing and any abatement required. | No survey on file. If contractor comes into contact with material suspected of containing lead or asbestos, please contact the Contracting Officer to initiate testing.
13 | 2026-04-28 |  | Please confirm if a single, duly-qualified individual may "triple hat" and serve as the proejct Superintendent, QC Manager, and SSHO. | QC should be separate individual.
14 | 2026-04-28 |  | Please provide a quantity or percentage of purlins replacement for contractors to include in their proposal. | Plan on at lease 25% of the entire area of the roof system.
15 | 2026-04-28 |  | Please provide information on the solar panel array that contractors are required to remove/replace. Please provide mounting method and circuit connections. | Removal and disposal
16 | 2026-04-28 |  | Please confirm that contrctors are to remove and reinstall the existing solar panels, and that new solar panels are not required. | Removal and disposal. No replacment needed.
17 | 2026-04-28 |  | Are there drawings available for the solar panels? | No
18 | 2026-04-28 |  | Can the Government provide updated drawings that include metal roof structure? | Yes, We have as-built drawings available for viewing. See attached drawing files
19 | 2026-04-28 |  | Is Fall Protection to be installed? | Yes
20 | 2026-04-28 |  | Are there specific approved or preferred metal manufacturers for this project? If so, please provide list of manufacturers and product specs. | All work must adhere to the installation standards specified in the 'Hurlburt_AFB_IFS_Pre-Final' document, specifically regarding material thickness, color, style, slope and type.
21 | 2026-04-28 |  | Is debris to be removed from site daily or will roll-off dumpsters be authorized until full and hauled off? | Debris can be hauled off when roll-off is full. Should be secured at all times.
22 | 2026-04-28 |  | Is contract limited to seven (7) weather days or will additional weather be granted based on adverse weather conditions? | The work-time analysis includes 7 days, however, additional days can be added to the PoP for documented adverse weather.
23 | 2026-04-28 |  | Please clarify change order process and allowable time frame for approval when deteriorated or concealed components are discovered during demo (rotten wood, damaged metal decking, wood nailers, etc.) | Contractor shall notify the Contracting Officer of any differing site condition IAW Clause 52.236-2. If change order is required, the Government will obtain necessary funding and issue a change order for additional work. May take up to 2 weeks or longer depending on the scope and dollar amount.
24 | 2026-04-28 |  | Blank
25 | 2026-04-28 |  | Is contractor responsible for required tree removal and any applicable forestry setback requirements ? | No, 1 SOCES will provide tree removal if required. Notify Contracting Officer if removal is needed.
26 | 2026-04-28 |  | Should the contractor included cost or allowance for damaged purlins? If so, what percentage should be used? | Yes, plan on at lease 25% of the entire area of the roof system.
27 | 2026-04-28 |  | Scope requires replaceing insulation. It appears there is no insulation below roof panels. Please confirm. | If there is no insulation provided with new.
28 | 2026-04-28 |  | There are no front-end specs for QC, Safety, submittals, schedule. Please provide. | None
29 | 2026-04-28 |  | Is U.S. Citizen mandatory at the job site? | NO, not required. However, any non-U.S. citizen will need to be submitted at least 14 days prior to needing access. Specific information to be provided at Pre-CON / kick-off meeting.
30 | 2026-04-28 |  | Are photos from site visit available? | Any pictures taken at the site visit were by contractors or subs in attendance.
31 | 2026-04-28 |  | Is this RFP required for the FF&E | No
32 | 2026-04-28 |  | For proposal submission, is PIEE mandatory or is email accepted. | Section 11.3 of the TOPR provides three methods for submission. Email is NOT authorized.
33 | 2026-04-28 |  | Is incumbent contractor's information available? | Previous roof was installed 20+ years ago. That contractors information is not available.
34 | 2026-04-28 |  | Is the contractor required to include a design with proposal package? | No
35 | 2026-04-30 |  | Is this a design-build effort? | No it is not a design build effort. The project will leverage the current structural support system for the new roof installation. Any structural members exhibiting significant damage will be replaced as necessary.
36 | 2026-04-30 |  | Regarding the fascia and soffit, could you please provide additional details, drawings, photos, or any other available information to verify the type of metal beams, quantities, etc., to be replaced? | We only have as-built that we can share.
37 | 2026-04-30 |  | Could you please provide us with the name of the company which originally installed the Solar Panels? | The company is unknown, we decided to demolish the arrray system and dispose.
38 | 2026-04-30 |  | Regarding the Lightning Protection system: the request is to dismantle and store it for reuse; however, the reinstallation requirements specify adding new components if necessary. Does this imply, then, that we are dealing with a new system in order to obtain certification? | Yes, Offer shall include replacement and new lightning Protection system to be installed
39 | 2026-04-30 |  | Please advise if the government anticipates any mechanical work as part of the re-roofing? | No
40 | 2026-05-06 |  | Due to the missing information regarding roof pitches and field dimensions, can the government provide a Roof R report. | All work must adhere to the installation standards specified in the 'Hurlburt_AFB_IFS_Pre-Final' document, specifically regarding material thickness, color, style, slope and type.